## Tidplan
Tidplan KO-byte (mall) 2023-06-01 ver 1.0
Aktiviteter |  | Månad 1 |  |  |  | Månad 2 |  |  |  | Månad 3 |  |  |  | Månad 4 |  |  |  | Månad 5 |  |  |  | Månad 6 |  |  |  | Månad 7
|  | vecka 1 | vecka 2 | vecka 3 | vecka 4 | vecka 5 | vecka 6 | vecka 7 | vecka 8 | vecka 9 | vecka 10 | vecka 11 | vecka 12 | vecka 13 | vecka 14 | vecka 15 | vecka 16 | vecka 17 | vecka 18 | vecka 19 | vecka 20 | vecka 21 | vecka 22 | vecka 23 | vecka 24 | vecka 25 | vecka 26 | vecka 27 | vecka 28
1. | Förarbeten KO-avtal
1.1 | Hantera upphandlingsprocess
2. | KO-avtal tecknat
2.1 | Informera om nytt avtal
3. | Migreringsprojekt påbörjas
3.1 | Uppstart migreringsprojekt
4. | Migreringsprojekt Projektplan migrering
4.1 | Ta fram projektplan
4.2 | Ta fram kommunikationsplan
5. | Migreringsprojekt Dataöverföring
5.1 | Överför Nätdata
5.2 | Överför Tjänstedata
6. | Migreringsprojekt Tjänsteförändringar
6.1 | Sammanställ Tjänsteförändringar
7. | Migreringsprojekt Information om förändringar
7.1 | Informera slutkund om förändringar i tjänsten
8. | Migrering och frysperiod
8.1 | Beställnings- och provisioneringsstopp
8.2 | Migrering av slutkunder
8.3 | Nedkoppling av slutkunder
9. | Kontaktinformation avtal, support och felanmälan
9.1 | Stäm av kundstock
10. | Avslut KO-byte

## Aktiviteter
Aktivitetslista från processbeskrivning KO-byte
Nr. | Aktivitet | Beskrivning
1 | Förarbeten KO-avtal | Upphandlingsprocess
2 | KO-avtal tecknat | Informationsaktiviteter
3 | Migreringsprojekt påbörjas | Projektstart
4 | Migreringsprojekt Projektplan migrering | Projektplanering
5 | Migreringsprojekt Dataöverföring | Överföring Nätdata och Tjänstedata
6 | Migreringsprojekt Tjänsteförändringar | Identifiera tjänsteförändringar
7 | Migreringsprojekt Information om förändringar | Informera om tjänsteförändringar
8 | Migrering och frysperiod | Genomförande av migreringar
9 | Kontaktinformation avtal, support och felanmälan | Avstämning kundstock och kontaktvägar
10 | Avslut KO-byte | Projekt avslutas

## Mall 4 v sprint (hidden)
|  |  | Vecka |  |  |  |  | Vecka |  | 1 |  |  | Vecka |  | 2 |  |  | Vecka |  | 3 |  |  | Vecka |  | 4 |  |  | Vecka |  | 4 |  |  | Vecka |  | 5
|  |  | Må | Ti | On | To | Fr | Må | Ti | On | To | Fr | Må | Ti | On | To | Fr | Må | Ti | On | To | Fr | Må | Ti | On | To | Fr | Må | Ti | On | To | Fr | Må | Ti | On | To | Fr
Inför kommande sprint
Per kort som ligger i Trello (alla)
Specificera användarscenarios för besökare
Specificera användarscenarios för redaktörer
Prioritera korten
Utifrån användarscenarios skapa funktionsspecifikationer för utvecklingen
Göra ett första estimat av respektive kort
Sprintstart | bar: Vecka Må to 5 Fr
Planera och besluta vilka kort som ska ingå i sprinten | bar: 1 On
Hur lång är sprinten? | bar: 1 On
När är genomgång av utvecklat (demo)? | bar: 1 On
Hur lång testperiod har Ledarna? | bar: 1 On
När ska justeringar utföras? | bar: 1 On
När ska sprinten vara accepterad? | bar: 1 On
När är kodstopp inför installation? | bar: 1 On
När ska installationen ske? | bar: 1 On
Hur många timmar finns tillgängliga? | bar: 1 On
Planera vilka moment/kort som ska utföras inom sprinten | bar: 1 On
Gå igenom utvalda kort för att se att inga direkt oklarheter finns | bar: 1 On
Revidera estimate av utvalda kort | bar: 1 On
Prioritera utvalda kort/moment | bar: 1 On
Genomförande av sprint | bar: Vecka Må to 5 Fr
Utveckling av planerade moment/kort enligt prioritering | bar: 1 On
Regelbundna avstämningar
nearU per dag | bar: 1 To to Vecka Ti
Projektgruppen per vecka | bar: 2 On; 3 On; 4 On; 4 On
Code review | bar: Vecka Må; Vecka Må; Vecka Må; Vecka Må; Vecka Må
nearU funktionstester | bar: 2 On to 2 To; 3 On to 3 To; 4 On to 4 To; 4 On to 4 To
Justeringar efter funktionstester | bar: 3 To
Installation på kundtest/stage (?) | bar: 3 Fr
Test och acceptans | bar: Vecka Må to 5 Fr
Demo/genomgång av nya mallar och funktioner som ingår i sprinten | bar: 3 On; Vecka Må
Ledarna acceptanstestar | bar: Vecka Ti to 4 Fr; Vecka Ti to 4 On
Viss kommunikation sker löpande när testerna genomförs | bar: 4 On to 4 Fr; 4 On
Ledarna sammanställer felrapporter | bar: 4 On to 4 Fr; 4 On
Justering och rättning görs | bar: 4 On
Ledarna utför omtester | bar: 4 On
Ledarna godkänner för installation | bar: 4 To
Kodstopp införs | bar: 4 To
Sprintslut
Installation i produktionsmiljö utförs | bar: Vecka Ti
nearU meddelar att installationen påbörjas | bar: Vecka Ti
nearU meddelar att installationen är slutförd | bar: Vecka Ti
Ledarna testar i produktionsmiljö | bar: Vecka Ti to 5 On
Övrigt, löpande och inte kopplat till en sprint
Dokumentation av editläget
Utbildningar

## Mall mer än 4 v sprint (hidden)
|  |  |  | Vecka |  |  |  |  | Vecka |  | 1 |  |  | Vecka |  | 2 |  |  | Vecka |  | 3 |  |  | Vecka |  | 4 |  |  | Vecka |  | 5 |  |  | Vecka |  | 6
|  |  |  | Må | Ti | On | To | Fr | Må | Ti | On | To | Fr | Må | Ti | On | To | Fr | Må | Ti | On | To | Fr | Må | Ti | On | To | Fr | Må | Ti | On | To | Fr | Må | Ti | On | To | Fr
Inför kommande sprint
Per kort som ligger i Trello (alla)
| Specificera användarscenarios för besökare |  | Ledarna
| Specificera användarscenarios för redaktörer |  | Ledarna
| Prioritera korten |  | Ledarna
| Utifrån användarscenarios skapa funktionsspecifikationer för utvecklingen |  | nearU
| Göra ett första estimat av respektive kort |  | nearU
Sprintstart |  |  | Alla | bar: Vecka Må to 6 Fr
Planera och besluta vilka kort som ska ingå i sprinten | bar: 1 On
| Hur lång är sprinten? |  | Alla | bar: 1 On
|  | När är genomgång av utvecklat (demo)? | Alla | bar: 1 On
|  | Hur lång testperiod har Ledarna? | Alla | bar: 1 On
|  | När ska justeringar utföras? | Alla | bar: 1 On
|  | När ska sprinten vara accepterad? | Alla | bar: 1 On
|  | När är kodstopp inför installation? | Alla | bar: 1 On
|  | När ska installationen ske? | Alla | bar: 1 On
| Hur många timmar finns tillgängliga? |  | nearU | bar: 1 On
| Planera vilka moment/kort som ska utföras inom sprinten |  | Alla | bar: 1 On
| Gå igenom utvalda kort för att se att inga direkt oklarheter finns |  | Alla | bar: 1 On
| Revidera estimate av utvalda kort |  | nearU | bar: 1 On
| Prioritera utvalda kort/moment |  | Ledarna | bar: 1 On
Genomförande av sprint | bar: Vecka Må to 6 Fr
| Utveckling av planerade moment/kort enligt prioritering |  | nearU | bar: 1 On
Regelbundna avstämningar
|  | nearU per dag | nearU | bar: 1 To to Vecka Ti
|  | Projektgruppen per vecka | Alla | bar: 2 On; 3 On; 4 On; 5 On
| Code review |  | nearU | bar: Vecka Må; Vecka Må; Vecka Må; Vecka Må; Vecka Må
| nearU funktionstester |  | nearU | bar: Vecka Må; 2 On to 2 To; Vecka Må to Vecka Ti; Vecka Må; 4 On to 4 To; Vecka Må; 5 On to 5 To
| Justeringar efter funktionstester |  | nearU | bar: 2 To; Vecka Ti
| Installation på kundtest/stage (?) |  | nearU | bar: 3 On
Test och acceptans | bar: Vecka Må to 6 Fr
| Demo/genomgång av nya mallar och funktioner som ingår i sprinten |  | Alla | bar: 3 On
| Ledarna acceptanstestar |  | Ledarna | bar: 3 To; Vecka Ti to 5 On
|  | Viss kommunikation sker löpande när testerna genomförs | Alla | bar: Vecka Ti to 5 On
|  | Ledarna sammanställer felrapporter | Ledarna | bar: Vecka Ti to 5 On
|  | Justering, rättning och interntester görs | nearU | bar: 4 To to 5 On
|  | Ledarna utför omtester | Ledarna | bar: 4 To to 5 On
| Ledarna godkänner för installation |  | Ledarna | bar: 5 To
| Kodstopp införs |  | nearU | bar: 5 To
Sprintslut
| Installation i produktionsmiljö utförs |  | nearU | bar: Vecka Ti
|  | nearU meddelar att installationen påbörjas | nearU | bar: Vecka Ti
|  | nearU meddelar att installationen är slutförd | nearU | bar: Vecka Ti
| Ledarna testar i produktionsmiljö |  | Ledarna | bar: Vecka Ti to 6 On
Övrigt, löpande och inte kopplat till en sprint
Dokumentation av editläget
Utbildningar

## Sprintplanering 2020_OLD (hidden)
Tidplan - Förvaltning
Lönekollen | December |  |  |  | Januari |  |  |  |  | Februari
Aktiviteter | 49 | 50 | 51 | 52 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9
Sprintplanering
Utveckling
Sprintdemo
Leveranstest (Ledarna)
Fixlistor klara
Implementera fixar (Visma)
Stickprov (Gunilla) | [6 empty] | 2018-01-17
Installation | [7 empty] | 2018-01-22
Lansering | [10 empty] | 2018-02-14
Program1-releasen | December |  |  |  | Januari |  |  |  |  | Februari
Aktiviteter Sprint 3 | 49 | 50 | 51 | 52 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9
Sprintplanering
Utveckling
Sprintdemo
Leveranstest (Ledarna) | [5 empty] | 2019-01-11
Fixlistor klara
Implementera fixar (Visma)
Acceptanstest (verksamheten)
Systemtest (Visma) | [6 empty] | 2018-01-10
Leveranstest (Ledarna/IT) | [6 empty] | 2018-01-11
Acceptanstest (listor & rapporter) | [9 empty] | 2018-02-05
Regressionstester (allt) | [9 empty] | 2019-02-06
Code stop | [10 empty] | 2019-02-11
Go-live förberedelser | [10 empty] | 15-18 feb
Installation | [11 empty] | 2018-02-19
| December |  |  |  | Januari |  |  |  |  | Februari |  |  |  | Mars |  |  |  | April |  |  |  | Maj |  |  |  |  | Juni | Maj |  |  |  |  | Maj
Aktiviteter Sprint 4 | 49 | 50 | 51 | 52 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 18 | 19 | 20 | 21 | 22 | 18 | 19 | 20 | 21 | 22 | 21 | 22 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21
Sprintplanering
Utveckling
Sprintdemo | [17 empty] | 2019-04-02
Leveranstest (Ledarna) | [18 empty] | 2019-04-12
Fixlistor klara | [18 empty] | 2019-04-12
Implementera fixar (Visma)
Acceptanstest (verksamheten) | [17 empty] | Carola | Carola
Code stop | [19 empty] | 2019-04-17
Installation | [20 empty] | 2019-04-24
| December |  |  |  | Januari |  |  |  |  | Februari |  |  |  | Mars |  |  |  | April |  |  |  | Maj |  |  |  |  | Juni |  |  |  | Juli |  |  |  | Augusti
Aktiviteter Sprint 5 | 49 | 50 | 51 | 52 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35
Sprintplanering | [19 empty] | 2019-04-16
Utveckling | [22 empty] | 2019-05-07
Sprintdemo | [23 empty] | 2019-05-09
Leveranstest (Ledarna) | [24 empty] | 2019-05-24
Fixlistor klara | [24 empty] | 2019-05-24
Implementera fixar (Visma)
Acceptanstest (verksamheten)
Code stop | [25 empty] | 2019-05-29
Installation | [26 empty] | 2019-06-03
| December |  |  |  | Januari |  |  |  |  | Februari |  |  |  | Mars |  |  |  | April |  |  |  | Maj |  |  |  |  | Juni |  |  |  | Juli |  |  |  | Augusti
Aktiviteter Sprint 6 | 49 | 50 | 51 | 52 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35
Sprintplanering | [24 empty] | 23 maj
Utveckling | [27 empty] | 13 juni
Sprintdemo | [28 empty] | 17 juni
Leveranstest (Ledarna) | [29 empty] | 24 juni
Fixlistor klara | [29 empty] | 24 juni
Implementera fixar (Visma)
Acceptanstest (verksamheten)
Code stop | [29 empty] | 27 juni
Installation | [30 empty] | 2 juli
| December |  |  |  | Januari |  |  |  |  | Februari |  |  |  | Mars |  |  |  | April |  |  |  | Maj |  |  |  |  | Juni |  |  |  | Juli |  |  |  | Augusti |  |  |  |  | September
Aktiviteter Sprint 7 | 49 | 50 | 51 | 52 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 |  |  |  |  | 37 |  |  |  |  | 38
Sprintplanering | [29 empty] | 2019-06-25
Utveckling | [33 empty] | 26 juli |  | Stefan
Sprintdemo | [37 empty] | 2019-08-20
Leveranstest (Ledarna) | [38 empty] | 2019-08-30
Fixlistor klara | [38 empty] | 2019-08-30
Implementera fixar (Visma)
Acceptanstest (verksamheten)
Code stop | [41 empty] | 4
Installation | [44 empty] | 9
Retro | [45 empty] | 10
Semester | 49 | 50 | 51 | 52 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35
Nina | [30 empty] | 4-5 juli |  |  |  |  | 5-7 aug
Deniz
Linda
Magnus
Helen | [30 empty] | Sem 3/7 |  |  |  | Sem 5-6/8
Fredrik
Stefan
| December |  |  |  | Januari |  |  |  |  | Februari |  |  |  | Mars |  |  |  | April |  |  |  | Maj |  |  |  |  | Juni |  |  |  | Juli |  |  |  | Augusti |  |  |  |  | September | [19 empty] | Oktober | [12 empty] | Höstlov
Aktiviteter Sprint 8 | 49 | 50 | 51 | 52 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 |  |  |  |  | 37 |  |  |  |  | 38 |  |  |  |  | 39 |  |  |  |  | 40 |  |  |  |  | 41 |  |  |  | 42 |  | 43 |  | 44
Sprintplanering | [40 empty] | 3
Utveckling | [41 empty] | 4 | [13 empty] | 24
Sprintdemo | [57 empty] | 26
Leveranstest (Ledarna) | [57 empty] | 26 |  |  |  |  | 3
Fixlistor klara | [62 empty] | 3
Implementera fixar (Visma) | [57 empty] | 26 | [7 empty] | 8
Acceptanstest (verksamheten)
Code stop | [65 empty] | 8
Installation | [66 empty] | 10
Retro | [69 empty] | 15
| December |  |  |  | Januari |  |  |  |  | Februari |  |  |  | Mars |  |  |  | April |  |  |  | Maj |  |  |  |  | Juni |  |  |  | Juli |  |  |  | Augusti |  |  |  |  | September | [19 empty] | Oktober | [12 empty] | Höstlov |  |  | November
Aktiviteter Sprint 9 | 49 | 50 | 51 | 52 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 |  |  |  |  | 37 |  |  |  |  | 38 |  |  |  |  | 39 |  |  |  |  | 40 |  |  |  |  | 41 |  |  |  | 42 |  | 43 |  | 44 |  |  | 45 |  |  |  | 46 |  |  | 47 | 48
Sprintplanering | [60 empty] | 1
Utveckling | [67 empty] | 11 |  |  |  | 24
Sprintdemo | [73 empty] | 29
Leveranstest (Ledarna) | [74 empty] | 30 |  | 6
Fixlistor klara | [76 empty] | 6
Implementera fixar (Visma) | [74 empty] | 30 |  |  |  | 8
Acceptanstest (verksamheten)
Code stop | [78 empty] | 8
Installation | [80 empty] | 12
Retro | [80 empty] | 12
| December |  |  |  | Januari |  |  |  |  | Februari |  |  |  | Mars |  |  |  | April |  |  |  | Maj |  |  |  |  | Juni |  |  |  | Juli |  |  |  | Augusti |  |  |  |  | September | [19 empty] | Oktober | [12 empty] | Höstlov |  |  | November | [9 empty] | December
Aktiviteter Sprint 10 | 49 | 50 | 51 | 52 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 |  |  |  |  | 37 |  |  |  |  | 38 |  |  |  |  | 39 |  |  |  |  | 40 |  |  |  |  | 41 |  |  |  | 42 |  | 43 |  | 44 |  |  | 45 |  |  |  | 46 |  |  | 47 | 48 |  | 49 |  |  | 50 |  | 51 |  |  | 52
Sprintplanering | [77 empty] | 7 | [17 empty] | Lågprio behövs
Utveckling | [81 empty] | 13
Sprintdemo | [84 empty] | 26
Leveranstest (Ledarna) | [84 empty] | 26 |  |  | 4
Fixlistor klara | [87 empty] | 4
Implementera fixar (Visma) | [84 empty] | 26 |  |  |  | 9
Acceptanstest (verksamheten)
Code stop | [88 empty] | 9
Installation | [89 empty] | 12
Retro | [91 empty] | 17
| December |  |  |  | Januari |  |  |  |  | Februari |  |  |  | Mars |  |  |  | April |  |  |  | Maj |  |  |  |  | Juni |  |  |  | Juli |  |  |  | Augusti |  |  |  |  | September | [19 empty] | Oktober | [12 empty] | Höstlov |  |  | November | [9 empty] | December | [8 empty] | Januari | [13 empty] | Februari | [8 empty] | Sportlov |  | Mars | [8 empty] | April
Aktiviteter Sprint 11 | 49 | 50 | 51 | 52 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 |  |  |  |  | 37 |  |  |  |  | 38 |  |  |  |  | 39 |  |  |  |  | 40 |  |  |  |  | 41 |  |  |  | 42 |  | 43 |  | 44 |  |  | 45 |  |  |  | 46 |  |  | 47 | 48 |  | 49 |  |  | 50 |  | 51 |  |  | 52 | 1 |  | 2 |  |  |  | 3 |  |  |  | 4 |  | 5 |  | 6 |  |  | 7 |  |  |  | 8 |  | 9 |  | 10 |  |  | 11 |  |  | 12 |  | 13 | 14
Sprintplanering | [86 empty] | 3
Utveckling | [88 empty] | 9 |  |  |  | 20
Sprintdemo | [97 empty] | 7
Leveranstest (Ledarna) | [97 empty] | 7 |  | 9 |  |  | 15
Fixlistor klara | [102 empty] | 15
Implementera fixar (Visma) | [98 empty] | 8 |  |  |  |  | 17
Acceptanstest (verksamheten)
Code stop | [104 empty] | 20
Installation | [105 empty] | 23
Retro | [105 empty] | 23
| December |  |  |  | Januari |  |  |  |  | Februari |  |  |  | Mars |  |  |  | April |  |  |  | Maj |  |  |  |  | Juni |  |  |  | Juli |  |  |  | Augusti |  |  |  |  | September | [19 empty] | Oktober | [12 empty] | Höstlov |  |  | November | [9 empty] | December | [8 empty] | Januari | [13 empty] | Februari | [8 empty] | Sportlov |  | Mars | [8 empty] | April
Aktiviteter Sprint 12 (inkl Lönekollen) | 49 | 50 | 51 | 52 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 |  |  |  |  | 37 |  |  |  |  | 38 |  |  |  |  | 39 |  |  |  |  | 40 |  |  |  |  | 41 |  |  |  | 42 |  | 43 |  | 44 |  |  | 45 |  |  |  | 46 |  |  | 47 | 48 |  | 49 |  |  | 50 |  | 51 |  |  | 52 | 1 |  | 2 |  |  |  | 3 |  |  |  | 4 |  | 5 |  | 6 |  |  | 7 |  |  |  | 8 |  | 9 |  | 10 |  |  | 11 |  |  | 12 |  | 13 | 14
Sprintplanering | [101 empty] | 14
Utveckling | [104 empty] | 20 |  |  | 31
Sprintdemo | [109 empty] | 4
Leveranstest (Ledarna) | [109 empty] | 4 |  |  |  | 12
Fixlistor klara | [113 empty] | 12
Implementera fixar (Visma) | [110 empty] | 5 |  |  |  | 14
Acceptanstest (verksamheten)
Code stop | [115 empty] | 17
Installation | [116 empty] | 20
Retro | [116 empty] | 20
| December |  |  |  | Januari |  |  |  |  | Februari |  |  |  | Mars |  |  |  | April |  |  |  | Maj |  |  |  |  | Juni |  |  |  | Juli |  |  |  | Augusti |  |  |  |  | September | [19 empty] | Oktober | [12 empty] | Höstlov |  |  | November | [9 empty] | December | [8 empty] | Januari | [13 empty] | Februari | [8 empty] | Sportlov |  | Mars | [8 empty] | April
Aktiviteter Sprint 13 | 49 | 50 | 51 | 52 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 |  |  |  |  | 37 |  |  |  |  | 38 |  |  |  |  | 39 |  |  |  |  | 40 |  |  |  |  | 41 |  |  |  | 42 |  | 43 |  | 44 |  |  | 45 |  |  |  | 46 |  |  | 47 | 48 |  | 49 |  |  | 50 |  | 51 |  |  | 52 | 1 |  | 2 |  |  |  | 3 |  |  |  | 4 |  | 5 |  | 6 |  |  | 7 |  |  |  | 8 |  | 9 |  | 10 |  |  | 11 |  |  | 12 |  | 13 | 14
Sprintplanering | [112 empty] | 11
Utveckling | [115 empty] | 17 |  |  | 28
Sprintdemo | [120 empty] | 4
Leveranstest (Ledarna) | [120 empty] | 4 |  |  | 12
Fixlistor klara | [123 empty] | 12
Implementera fixar (Visma) | [121 empty] | 5 |  |  | 14
Acceptanstest (verksamheten)
Code stop | [125 empty] | 17
Installation | [126 empty] | 20
Retro | [126 empty] | 20
Note on H23: ====== ID#AAAAECA_1ys tc={573DDB3F-70FC-4C9A-A84B-55C91BB401E6} (2019-12-23 09:07:13) [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: listor & rapporter Reply: Deniz på halvtid från v9
Note on N4: ====== ID#AAAAECA_1vo Nina Malm (2019-12-23 09:07:13) Sportlov
Note on N16: ====== ID#AAAAECA_1wQ Nina Malm (2019-12-23 09:07:13) Sportlov
Note on N33: ====== ID#AAAAECA_1uU Nina Malm (2019-12-23 09:07:13) Sportlov
Note on N45: ====== ID#AAAAECA_1uQ Nina Malm (2019-12-23 09:07:13) Sportlov
Note on N57: ====== ID#AAAAECA_1u0 Nina Malm (2019-12-23 09:07:13) Sportlov
Note on N69: ====== ID#AAAAECA_1vA Nina Malm (2019-12-23 09:07:13) Sportlov
Note on N81: ====== ID#AAAAECA_1v4 Nina Malm (2019-12-23 09:07:13) Sportlov
Note on N91: ====== ID#AAAAECA_1uA Nina Malm (2019-12-23 09:07:13) Sportlov
Note on N104: ====== ID#AAAAECA_1s0 Nina Malm (2019-12-23 09:07:13) Sportlov
Note on N117: ====== ID#AAAAECA_1s8 Nina Malm (2019-12-23 09:07:13) Sportlov
Note on N129: ====== ID#AAAAECA_1rg Nina Malm (2019-12-23 09:07:13) Sportlov
Note on N141: ====== ID#AAAAECA_1us Nina Malm (2019-12-23 09:07:13) Sportlov
Note on N153: ====== ID#AAAAECA_1s4 Nina Malm (2019-12-23 09:07:13) Sportlov
Note on P33: ====== ID#AAAAECA_1x4 tc={4B7EA7F9-551C-4EC2-94E7-427FCC6D643B} (2019-12-23 09:07:13) [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Magnus i Turkiet
Note on Q33: ====== ID#AAAAECA_1vI tc={6DC1A5A6-FE3B-4DB1-A08F-C6673AB4A3BB} (2019-12-23 09:07:13) [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Magnus i Turkiet
Note on R33: ====== ID#AAAAECA_1xU tc={BE7C3AEC-2768-4523-AE39-B46DC8C9770C} (2019-12-23 09:07:13) [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Magnus i Turkiet
Note on S40: ====== ID#AAAAECA_1rk tc={0D16E47D-B02A-4DE1-ADE9-11D5C4A4A109} (2019-12-23 09:07:13) [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Carola pga uppgradering av Epi
Note on U33: ====== ID#AAAAECA_1tg Nina Malm (2019-12-23 09:07:13) Påsklov
Note on U45: ====== ID#AAAAECA_1ro Nina Malm (2019-12-23 09:07:13) Påsklov
Note on U57: ====== ID#AAAAECA_1zQ Nina Malm (2019-12-23 09:07:13) Påsklov
Note on U69: ====== ID#AAAAECA_1zU Nina Malm (2019-12-23 09:07:13) Påsklov
Note on U81: ====== ID#AAAAECA_1tk Nina Malm (2019-12-23 09:07:13) Påsklov
Note on U91: ====== ID#AAAAECA_1tE Nina Malm (2019-12-23 09:07:13) Påsklov
Note on U104: ====== ID#AAAAECA_1xA Nina Malm (2019-12-23 09:07:13) Påsklov
Note on U117: ====== ID#AAAAECA_1yM Nina Malm (2019-12-23 09:07:13) Påsklov
Note on U129: ====== ID#AAAAECA_1xI Nina Malm (2019-12-23 09:07:13) Påsklov
Note on U141: ====== ID#AAAAECA_1ss Nina Malm (2019-12-23 09:07:13) Påsklov
Note on U153: ====== ID#AAAAECA_1yU Nina Malm (2019-12-23 09:07:13) Påsklov
Note on W45: ====== ID#AAAAECA_1zA tc={34823EBC-C112-4667-A98E-814E132D6049} (2019-12-23 09:07:13) [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Valborg/Första maj
Note on W57: ====== ID#AAAAECA_1vc tc={26F715D4-64A4-4017-8722-CFE6105DD599} (2019-12-23 09:07:13) [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Valborg/Första maj
Note on W69: ====== ID#AAAAECA_1yg tc={B27F9634-39A3-48A7-9095-0413D617D5DE} (2019-12-23 09:07:13) [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Valborg/Första maj
Note on W81: ====== ID#AAAAECA_1sk tc={D4F65651-7473-4C81-9F26-771FCC6A5AFA} (2019-12-23 09:07:13) [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Valborg/Första maj
Note on W91: ====== ID#AAAAECA_1yc tc={5518147B-C3A8-4389-BDA5-AB473763DCB5} (2019-12-23 09:07:13) [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Valborg/Första maj
Note on W104: ====== ID#AAAAECA_1y0 tc={790533AC-3343-4083-866D-E3A5F3178BA8} (2019-12-23 09:07:13) [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Valborg/Första maj
Note on W117: ====== ID#AAAAECA_1xs tc={63E5E907-3B34-4E33-8FA3-5B58AD73F179} (2019-12-23 09:07:13) [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Valborg/Första maj
Note on W129: ====== ID#AAAAECA_1vE tc={29CA4E6A-1AB5-4555-A699-52FA8F368935} (2019-12-23 09:07:13) [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Valborg/Första maj
Note on W141: ====== ID#AAAAECA_1xk tc={B7674FAF-A69D-4992-844D-DFE47B994557} (2019-12-23 09:07:13) [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Valborg/Första maj
Note on W153: ====== ID#AAAAECA_1yA tc={19364529-6766-47AE-8B4A-742322C6C119} (2019-12-23 09:07:13) [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Valborg/Första maj
Note on AA45: ====== ID#AAAAECA_1yI tc={62DE2A1E-D9BD-4261-83E5-1B18B4059BD6} (2019-12-23 09:07:13) [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Kristi himm + klämdag
Note on AA57: ====== ID#AAAAECA_1ws tc={B052354D-058B-44A9-9814-C1905C2E3C5B} (2019-12-23 09:07:13) [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Kristi himm + klämdag
Note on AA69: ====== ID#AAAAECA_1tQ tc={34517DA9-CE1E-46D9-AD99-B775C90FB464} (2019-12-23 09:07:13) [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Kristi himm + klämdag
Note on AA81: ====== ID#AAAAECA_1zI tc={71759A64-7969-4D2F-9F67-233D496B1D7B} (2019-12-23 09:07:13) [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Kristi himm + klämdag
Note on AA91: ====== ID#AAAAECA_1tY tc={3EC927C0-DCCC-449F-AD2D-F9B5665F4BBB} (2019-12-23 09:07:13) [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Kristi himm + klämdag
Note on AA104: ====== ID#AAAAECA_1sM tc={96CF70E9-29A3-4FAD-87BD-02DCB645B649} (2019-12-23 09:07:13) [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Kristi himm + klämdag
Note on AA117: ====== ID#AAAAECA_1w8 tc={89DBECF4-E310-4E62-A9A0-277A1126E7CD} (2019-12-23 09:07:13) [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Kristi himm + klämdag
Note on AA129: ====== ID#AAAAECA_1w4 tc={60A34789-BCEA-421A-BC4C-0281DB5B4CBF} (2019-12-23 09:07:13) [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Kristi himm + klämdag
Note on AA141: ====== ID#AAAAECA_1xY tc={D7AA981C-E1E8-42CC-A53C-81508F1D5F87} (2019-12-23 09:07:13) [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Kristi himm + klämdag
Note on AA153: ====== ID#AAAAECA_1tU tc={1CD29F4C-A40B-4F87-A837-D312E1DE585F} (2019-12-23 09:07:13) [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Kristi himm + klämdag
Note on AB45: ====== ID#AAAAECA_1sw tc={AE3833DF-8994-4ACF-82E8-8762BE3E90DD} (2019-12-23 09:07:13) [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Nationaldag + klämdag
Note on AB57: ====== ID#AAAAECA_1xM tc={016123C0-37C8-483A-A031-DCAC605D9B8C} (2019-12-23 09:07:13) [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Nationaldag + klämdag
Note on AB69: ====== ID#AAAAECA_1wc tc={2B1D1CAE-6587-47CB-985A-06A33361D018} (2019-12-23 09:07:13) [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Nationaldag + klämdag
Note on AB81: ====== ID#AAAAECA_1yo tc={66BFD522-7A5B-4AF3-85EC-0344AE69C636} (2019-12-23 09:07:13) [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Nationaldag + klämdag
Note on AB91: ====== ID#AAAAECA_1wU tc={0C8237BE-C591-4E7D-B886-29454E2FE939} (2019-12-23 09:07:13) [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Nationaldag + klämdag
Note on AB104: ====== ID#AAAAECA_1vQ tc={8F72420F-D075-4496-B85C-FF2D2C5F1424} (2019-12-23 09:07:13) [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Nationaldag + klämdag
Note on AB117: ====== ID#AAAAECA_1tw tc={2A285DE4-16CB-46CE-B246-E1ADDC216E43} (2019-12-23 09:07:13) [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Nationaldag + klämdag
Note on AB129: ====== ID#AAAAECA_1vk tc={8D6D2696-7889-4071-A5E0-0720765B1B7A} (2019-12-23 09:07:13) [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Nationaldag + klämdag
Note on AB141: ====== ID#AAAAECA_1uo tc={DA472342-61D8-4139-B92D-B8C851116FDD} (2019-12-23 09:07:13) [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Nationaldag + klämdag
Note on AB153: ====== ID#AAAAECA_1vU tc={77D545C9-943B-4818-8F67-96FE473DE3A8} (2019-12-23 09:07:13) [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Nationaldag + klämdag
Note on AD45: ====== ID#AAAAECA_1vM tc={93B6458D-3AB7-4B03-A65A-080218FC940D} (2019-12-23 09:07:13) [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Midsommarafton
Note on AD57: ====== ID#AAAAECA_1wM tc={2C7FBDCF-5D2C-4267-8D09-557218480921} (2019-12-23 09:07:13) [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Midsommarafton
Note on AD69: ====== ID#AAAAECA_1yY tc={DD676937-3C24-4481-BDC1-945434E4A925} (2019-12-23 09:07:13) [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Midsommarafton
Note on AD81: ====== ID#AAAAECA_1r8 tc={609B214D-65AC-4EBD-BE0C-90E1A9814324} (2019-12-23 09:07:13) [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Midsommarafton
Note on AD91: ====== ID#AAAAECA_1x0 tc={80BA9CB2-C482-447E-8830-F35F9D8231FC} (2019-12-23 09:07:13) [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Midsommarafton
Note on AD104: ====== ID#AAAAECA_1sg tc={ECB7D4F9-40D5-40B0-B78D-BE28D28FDE61} (2019-12-23 09:07:13) [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Midsommarafton
Note on AD117: ====== ID#AAAAECA_1vY tc={3BF76AA4-5FB2-4CC3-AAAD-BB16F5AD6FC2} (2019-12-23 09:07:13) [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Midsommarafton
Note on AD129: ====== ID#AAAAECA_1tc tc={DBD8DD96-3EB6-4824-98F0-30FDDE43B3D8} (2019-12-23 09:07:13) [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Midsommarafton
Note on AD141: ====== ID#AAAAECA_1sU tc={A330F930-8675-4C4C-9DC1-C86C97B64832} (2019-12-23 09:07:13) [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Midsommarafton
Note on AD153: ====== ID#AAAAECA_1u4 tc={4FA9D500-43A9-4B7F-BE3D-4312CE5C43A2} (2019-12-23 09:07:13) [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Midsommarafton

## Sprintplanering_old (hidden)
Tidplan - Förvaltning
Lönekollen | December |  |  |  | Januari |  |  |  |  | Februari
Aktiviteter | 49 | 50 | 51 | 52 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9
Sprintplanering
Utveckling
Sprintdemo
Leveranstest (Ledarna)
Fixlistor klara
Implementera fixar (Visma)
Stickprov (Gunilla) | [6 empty] | 2018-01-17
Installation | [7 empty] | 2018-01-22
Lansering | [10 empty] | 2018-02-14
Program1-releasen | December |  |  |  | Januari |  |  |  |  | Februari
Aktiviteter Sprint 3 | 49 | 50 | 51 | 52 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9
Sprintplanering
Utveckling
Sprintdemo
Leveranstest (Ledarna) | [5 empty] | 2019-01-11
Fixlistor klara
Implementera fixar (Visma)
Acceptanstest (verksamheten)
Systemtest (Visma) | [6 empty] | 2018-01-10
Leveranstest (Ledarna/IT) | [6 empty] | 2018-01-11
Acceptanstest (listor & rapporter) | [9 empty] | 2018-02-05
Regressionstester (allt) | [9 empty] | 2019-02-06
Code stop | [10 empty] | 2019-02-11
Go-live förberedelser | [10 empty] | 15-18 feb
Installation | [11 empty] | 2018-02-19
| December |  |  |  | Januari |  |  |  |  | Februari |  |  |  | Mars |  |  |  | April |  |  |  | Maj |  |  |  |  | Juni | Maj |  |  |  |  | Maj
Aktiviteter Sprint 4 | 49 | 50 | 51 | 52 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 18 | 19 | 20 | 21 | 22 | 18 | 19 | 20 | 21 | 22 | 21 | 22 | 20 | 21 | 22 | 21 | 20 | 21 | 22 | 21 | 22
Sprintplanering
Utveckling
Sprintdemo | [17 empty] | 2019-04-02
Leveranstest (Ledarna) | [18 empty] | 2019-04-12
Fixlistor klara | [18 empty] | 2019-04-12
Implementera fixar (Visma)
Acceptanstest (verksamheten) | [17 empty] | Carola | Carola
Code stop | [19 empty] | 2019-04-17
Installation | [20 empty] | 2019-04-24
| December |  |  |  | Januari |  |  |  |  | Februari |  |  |  | Mars |  |  |  | April |  |  |  | Maj |  |  |  |  | Juni |  |  |  | Juli |  |  |  | Augusti |  |  |  |  | September |  |  |  | Oktober
Aktiviteter Sprint 5 | 49 | 50 | 51 | 52 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44
Sprintplanering | [19 empty] | 2019-04-16
Utveckling | [22 empty] | 2019-05-07
Sprintdemo | [23 empty] | 2019-05-09
Leveranstest (Ledarna) | [24 empty] | 2019-05-24
Fixlistor klara | [24 empty] | 2019-05-24
Implementera fixar (Visma)
Acceptanstest (verksamheten)
Code stop | [25 empty] | 2019-05-29
Installation | [26 empty] | 2019-06-03
| December |  |  |  | Januari |  |  |  |  | Februari |  |  |  | Mars |  |  |  | April |  |  |  | Maj |  |  |  |  | Juni |  |  |  | Juli |  |  |  | Augusti |  |  |  |  | September |  |  |  | Oktober
Aktiviteter Sprint 6 | 49 | 50 | 51 | 52 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44
Sprintplanering | [24 empty] | 23 maj
Utveckling | [27 empty] | 13 juni
Sprintdemo | [28 empty] | 17 juni
Leveranstest (Ledarna) | [29 empty] | 24 juni
Fixlistor klara | [29 empty] | 24 juni
Implementera fixar (Visma)
Acceptanstest (verksamheten)
Code stop | [29 empty] | 27 juni
Installation | [30 empty] | 2 juli
| December |  |  |  | Januari |  |  |  |  | Februari |  |  |  | Mars |  |  |  | April |  |  |  | Maj |  |  |  |  | Juni |  |  |  | Juli |  |  |  | Augusti |  |  |  |  | September |  |  |  | Oktober
Aktiviteter Sprint 7 | 49 | 50 | 51 | 52 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44
Sprintplanering | [29 empty] | 2019-06-25
Utveckling | [33 empty] | 26 juli |  | Stefan
Sprintdemo | [37 empty] | 2019-08-20
Leveranstest (Ledarna) | [38 empty] | 2019-08-30
Fixlistor klara | [38 empty] | 2019-08-30
Implementera fixar (Visma)
Acceptanstest (verksamheten)
Code stop | [39 empty] | 2019-09-04
Installation | [40 empty] | 2019-09-09
| December |  |  |  | Januari |  |  |  |  | Februari |  |  |  | Mars |  |  |  | April |  |  |  | Maj |  |  |  |  | Juni |  |  |  | Juli |  |  |  | Augusti |  |  |  |  | September |  |  |  | Oktober
Aktiviteter Sprint 8 (UTKAST) | 49 | 50 | 51 | 52 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44
Sprintplanering | [39 empty] | 3 sep (tis)
Utvecklingsstart | [40 empty] | 10 sep (tis) |  | 23 sep (må)
Sprintdemo | [42 empty] | 26 sep (to)
Leveranstest (Ledarna) | [43 empty] | 3 okt (to)
Fixlistor klara | [43 empty] | 3 okt (to)
Implementera fixar (Visma)
Acceptanstest (verksamheten)
Code stop | [44 empty] | 8 okt
Installation | [44 empty] | 10 okt
Semester | 49 | 50 | 51 | 52 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44
Nina | [30 empty] | 4-5 juli |  |  |  |  | 5-7 aug
Deniz
Linda
Magnus
Helen | [30 empty] | Sem 3/7 |  |  |  | Sem 5-6/8
Fredrik
Stefan
Note on H23: ====== ID#AAAAECA_1xc tc={0332DB70-7DFC-44A6-BCE0-A78386496C8E} (2019-12-23 09:07:13) [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: listor & rapporter Reply: Deniz på halvtid från v9
Note on N4: ====== ID#AAAAECA_1wE Nina Malm (2019-12-23 09:07:13) Sportlov
Note on N16: ====== ID#AAAAECA_1r4 Nina Malm (2019-12-23 09:07:13) Sportlov
Note on N33: ====== ID#AAAAECA_1vg Nina Malm (2019-12-23 09:07:13) Sportlov
Note on N45: ====== ID#AAAAECA_1y4 Nina Malm (2019-12-23 09:07:13) Sportlov
Note on N57: ====== ID#AAAAECA_1t0 Nina Malm (2019-12-23 09:07:13) Sportlov
Note on N69: ====== ID#AAAAECA_1yk Nina Malm (2019-12-23 09:07:13) Sportlov
Note on N81: ====== ID#AAAAECA_1v8 Nina Malm (2019-12-23 09:07:13) Sportlov
Note on N92: ====== ID#AAAAECA_1xQ Nina Malm (2019-12-23 09:07:13) Sportlov
Note on P33: ====== ID#AAAAECA_1rs tc={0D7C6B6F-2C9F-4CFD-9606-086FE8FF2DA3} (2019-12-23 09:07:13) [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Magnus i Turkiet
Note on Q33: ====== ID#AAAAECA_1vw tc={6D5DEF6D-22CD-463B-A6AB-E6D2714C44E9} (2019-12-23 09:07:13) [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Magnus i Turkiet
Note on R33: ====== ID#AAAAECA_1wA tc={6D223C82-EE40-45DA-AFD1-31D8812B7C00} (2019-12-23 09:07:13) [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Magnus i Turkiet
Note on S40: ====== ID#AAAAECA_1wk tc={49A0C4F9-2B46-4510-86BC-4947565C0176} (2019-12-23 09:07:13) [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Carola pga uppgradering av Epi
Note on U33: ====== ID#AAAAECA_1x8 Nina Malm (2019-12-23 09:07:13) Påsklov
Note on U45: ====== ID#AAAAECA_1w0 Nina Malm (2019-12-23 09:07:13) Påsklov
Note on U57: ====== ID#AAAAECA_1sE Nina Malm (2019-12-23 09:07:13) Påsklov
Note on U69: ====== ID#AAAAECA_1ww Nina Malm (2019-12-23 09:07:13) Påsklov
Note on U81: ====== ID#AAAAECA_1yQ Nina Malm (2019-12-23 09:07:13) Påsklov
Note on U92: ====== ID#AAAAECA_1tM Nina Malm (2019-12-23 09:07:13) Påsklov
Note on W45: ====== ID#AAAAECA_1to tc={18543274-C604-4892-B4FD-305475673C8E} (2019-12-23 09:07:13) [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Valborg/Första maj
Note on W57: ====== ID#AAAAECA_1zE tc={2E828515-0FBE-4EA3-B512-0F21FCE957FF} (2019-12-23 09:07:13) [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Valborg/Första maj
Note on W69: ====== ID#AAAAECA_1uY tc={67FE5CDC-75C2-414E-BD3D-71C2E9533834} (2019-12-23 09:07:13) [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Valborg/Första maj
Note on W81: ====== ID#AAAAECA_1uM tc={F421D491-43D9-4086-BF9C-017B467E3451} (2019-12-23 09:07:13) [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Valborg/Första maj
Note on W92: ====== ID#AAAAECA_1wo tc={A3218782-0F5D-4D02-ABB3-A804BD727A03} (2019-12-23 09:07:13) [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Valborg/Första maj
Note on AA45: ====== ID#AAAAECA_1wg tc={27A90C3B-7BA1-4E19-8180-FCBBCC68AD6B} (2019-12-23 09:07:13) [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Kristi himm + klämdag
Note on AA57: ====== ID#AAAAECA_1r0 tc={958D72DD-295D-4F61-9FB6-6D8A91B356BF} (2019-12-23 09:07:13) [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Kristi himm + klämdag
Note on AA69: ====== ID#AAAAECA_1sA tc={1D59115A-056B-4F1A-9778-B8AF99A7BDDC} (2019-12-23 09:07:13) [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Kristi himm + klämdag
Note on AA81: ====== ID#AAAAECA_1uI tc={C6C459A7-80D3-431D-B469-B2289AB846CD} (2019-12-23 09:07:13) [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Kristi himm + klämdag
Note on AA92: ====== ID#AAAAECA_1yE tc={DE11A443-C5AC-41D7-8D4F-F6B617DF18E1} (2019-12-23 09:07:13) [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Kristi himm + klämdag
Note on AB45: ====== ID#AAAAECA_1xw tc={569C4F53-2FE6-454E-8FB6-996C85C62CCA} (2019-12-23 09:07:13) [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Nationaldag + klämdag
Note on AB57: ====== ID#AAAAECA_1sQ tc={7AA7A0A8-850B-4B98-B8CC-E354C0880A22} (2019-12-23 09:07:13) [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Nationaldag + klämdag
Note on AB69: ====== ID#AAAAECA_1uk tc={869B20A7-C020-436C-B228-4C6B14D80C0F} (2019-12-23 09:07:13) [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Nationaldag + klämdag
Note on AB81: ====== ID#AAAAECA_1xo tc={F6D4E8B2-7B72-4C86-9EA7-0C62AF3F4D36} (2019-12-23 09:07:13) [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Nationaldag + klämdag
Note on AB92: ====== ID#AAAAECA_1xg tc={A103FCFA-7B72-4AB7-A564-8C2B3331A8F7} (2019-12-23 09:07:13) [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Nationaldag + klämdag
Note on AD45: ====== ID#AAAAECA_1rw tc={2E939FE1-6E9C-4BA6-BE43-F5FBA29452E3} (2019-12-23 09:07:13) [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Midsommarafton
Note on AD57: ====== ID#AAAAECA_1sI tc={EA4099DF-B9CD-41A4-8DA8-82E0041D8585} (2019-12-23 09:07:13) [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Midsommarafton
Note on AD69: ====== ID#AAAAECA_1sY tc={7CE35114-8C48-4443-8495-8967DF0463F8} (2019-12-23 09:07:13) [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Midsommarafton
Note on AD81: ====== ID#AAAAECA_1vs tc={3D6011E7-00FB-4260-9A17-E865F10A9530} (2019-12-23 09:07:13) [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Midsommarafton
Note on AD92: ====== ID#AAAAECA_1uE tc={CB0A2966-7B6B-4F51-B2F3-E08047BA7DF6} (2019-12-23 09:07:13) [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Midsommarafton

## Årsplan (hidden)
| Januari |  |  |  |  | Februari |  |  |  | Mars |  |  |  | April |  |  |  |  | Maj |  |  |  | Juni
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26
Sprintplanering
Utveckling
Sprintdemo
Acceptanstest
Fixlistor klara
Implementera fixar
Code stop
Installation
| Juli |  |  |  | Augusti |  |  |  |  | September |  |  |  | Oktober |  |  |  |  | November |  |  |  | December
| 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52
Sprintplanering
Utveckling
Sprintdemo
Acceptanstest
Fixlistor klara
Implementera fixar
Code stop
Installation
| Sprint 3 |  | Sprint 4 |  | Sprint 5 |  | Sprint 6 |  | Sprint 7
| Lönekollen |  | Kurs & E
Note on J3: ====== ID#AAAAECA_1uc NiMa (2019-12-23 09:07:13) Sportlov Stockholm
Note on Q3: ====== ID#AAAAECA_1tA Nina Malm (2019-12-23 09:07:13) Påsklov Stockholm

## Mall- sprint 10 (hidden)
Sprint 2 |  |  |  | Vecka |  |  |  |  | Vecka 14 |  |  |  |  | Vecka 15 |  |  |  |  | Vecka 16 |  |  |  |  | Vecka 17 |  |  |  |  | Vecka 18 |  |  |  |  | Vecka 19 |  |  |  |  | Vecka 20 |  |  |  |  | Vecka 21 |  |  |  |  | Vecka 22 |  |  |  |  | Vecka 23 |  |  |  |  | Vecka 24
 | time axis 2018-04-02 to 2018-06-15
|  |  |  | Må | Ti | On | To | Fr | time axis 2018-04-02 to 2018-06-15
Inför kommande sprint
Per kort som ligger i Trello (alla)
| Specificera användarscenarios för besökare |  | Ledarna
| Specificera användarscenarios för redaktörer |  | Ledarna
| Prioritera korten |  | Ledarna
| Utifrån användarscenarios skapa funktionsspecifikationer för utvecklingen |  | nearU
| Göra ett första estimat av respektive kort |  | nearU
| Retrospective |  | nearU
Sprintstart |  |  | Alla | bar: 2018-04-02 to 2018-04-30; 2018-05-02 to 2018-06-15
Sprintplanering
| Hur lång är sprinten? |  | Alla | bar: 2018-05-02
|  | När är genomgång av utvecklat (demo)? | Alla | bar: 2018-05-02
|  | Hur lång testperiod har Ledarna? | Alla | bar: 2018-05-02
|  | När ska justeringar utföras? | Alla | bar: 2018-05-02
|  | När ska sprinten vara accepterad? | Alla | bar: 2018-05-02
|  | När är kodstopp inför installation? | Alla | bar: 2018-05-02
|  | När ska installationen ske? | Alla | bar: 2018-05-02
| Hur många timmar finns tillgängliga? |  | nearU | bar: 2018-05-02
| Planera vilka moment/kort som ska utföras inom sprinten |  | Alla | bar: 2018-05-02
| Gå igenom utvalda kort för att se att inga direkt oklarheter finns |  | Alla | bar: 2018-05-02
| Revidera estimate av utvalda kort |  | nearU | bar: 2018-05-02
| Prioritera utvalda kort/moment |  | Ledarna | bar: 2018-05-02
Genomförande av sprint | bar: 2018-04-02 to 2018-04-30; 2018-05-02 to 2018-06-15
| Utveckling av planerade moment/kort enligt prioritering |  | nearU | bar: 2018-05-02
Regelbundna avstämningar
|  | nearU per dag | nearU
|  | Projektgruppen per vecka | Alla
| Code review |  | nearU
| nearU funktionstester |  | nearU
| Justeringar efter funktionstester |  | nearU
| Installation på kundtest/stage (?) |  | nearU
Test och acceptans
| Demo/genomgång av nya mallar och funktioner som ingår i sprinten |  | Alla
| Ledarna acceptanstestar |  | Ledarna
|  | Viss kommunikation sker löpande när testerna genomförs | Alla | bar: 2018-04-02 to 2018-04-03
|  | Ledarna sammanställer felrapporter | Ledarna
|  | Justering, rättning och interntester görs | nearU | bar: 2018-04-02 to 2018-04-03
|  | Ledarna utför omtester | Ledarna | bar: 2018-04-02 to 2018-04-03
| Ledarna godkänner för installation |  | Ledarna | bar: 2018-04-03
| Kodstopp införs |  | nearU | bar: 2018-04-03
Sprintslut
| Installation i produktionsmiljö utförs |  | nearU | bar: 2018-04-04
|  | nearU meddelar att installationen påbörjas | nearU | bar: 2018-04-04
|  | nearU meddelar att installationen är slutförd | nearU | bar: 2018-04-04
| Ledarna testar i produktionsmiljö |  | Ledarna | bar: 2018-04-04 to 2018-04-05
Övrigt, löpande och inte kopplat till en sprint
Dokumentation av editläget
Utbildningar
Note on L47: ====== ID#AAAAECA_1u8 nearU (2019-12-23 09:07:13) Installation Sprint 10
Note on M47: ====== ID#AAAAECA_1sc nearU (2019-12-23 09:07:13) Refresh av Salesforce testlåda (blir en bra testa inför lanseringen)

## Mall - sprint master (hidden)
Sprint 9 |  |  |  | Vecka |  |  |  |  | Vecka 17 |  |  |  |  | Vecka 18 |  |  |  |  | Vecka 19 |  |  |  |  | Vecka 20 |  |  |  |  | Vecka 21 |  |  |  |  | Vecka 22 |  |  |  |  | Vecka 23 |  |  |  |  | Vecka 24 |  |  |  |  | Vecka 25 |  |  |  |  | Vecka 26 |  |  |  |  | Vecka 27 |  |  |  |  | Vecka 28 |  |  |  |  | Vecka 29 |  |  |  |  | Vecka 30 |  |  |  |  | Vecka 31 |  |  |  |  | Vecka 32 |  |  |  |  | Vecka 33 |  |  |  |  | Vecka 34 |  |  |  |  | Vecka 35 |  |  |  |  | Vecka 36 |  |  |  |  | Vecka 37 |  |  |  |  | Vecka 38 |  |  |  |  | Vecka 39 |  |  |  |  | Vecka 40 |  |  |  |  | Vecka 41 |  |  |  |  | Vecka 42 |  |  |  |  | Vecka 43 |  |  |  |  | Vecka 44 |  |  |  |  | Vecka 45 |  |  |  |  | Vecka 46 |  |  |  |  | Vecka 47 |  |  |  |  | Vecka 48 |  |  |  |  | Vecka 49 |  |  |  |  | Vecka 50 |  |  |  |  | Vecka 51 |  |  |  |  | Vecka 52
 | time axis 2017-04-24 to 2017-12-29
|  |  |  | Må | Ti | On | To | Fr | time axis 2017-04-24 to 2017-12-29
Inför kommande sprint | [8 empty] | 2017-08-24: KL; 2017-08-25: -------------------------------------------------------------->; 2017-09-18: ----- Acceptanstester ------
Per kort som ligger i Trello (alla)
| Specificera användarscenarios för besökare |  | Ledarna
| Specificera användarscenarios för redaktörer |  | Ledarna
| Prioritera korten |  | Ledarna
| Utifrån användarscenarios skapa funktionsspecifikationer för utvecklingen |  | nearU
| Göra ett första estimat av respektive kort |  | nearU
| Retrospective |  | nearU
Sprintstart |  |  | Alla | [5 empty] | 2017-05-31: x; 2017-08-17: P9; 2017-09-21: P10; 2017-10-18: Plan; 2017-10-25: Plan; 2017-11-22: x; 2017-11-29: x
Planera och besluta vilka kort som ska ingå i sprinten | bar: 2017-05-31
| Hur lång är sprinten? |  | Alla | bar: 2017-05-31; 2017-08-17; 2017-09-21; 2017-11-22; 2017-11-29
|  | När är genomgång av utvecklat (demo)? | Alla | bar: 2017-05-31; 2017-08-17; 2017-09-21; 2017-11-22; 2017-11-29
|  | Hur lång testperiod har Ledarna? | Alla | bar: 2017-05-31; 2017-08-17; 2017-09-21; 2017-11-22; 2017-11-29
|  | När ska justeringar utföras? | Alla | bar: 2017-05-31; 2017-08-17; 2017-09-21; 2017-11-22; 2017-11-29
|  | När ska sprinten vara accepterad? | Alla | bar: 2017-05-31; 2017-08-17; 2017-09-21; 2017-11-22; 2017-11-29
|  | När är kodstopp inför installation? | Alla | bar: 2017-05-31; 2017-08-17; 2017-09-21; 2017-11-22; 2017-11-29
|  | När ska installationen ske? | Alla | bar: 2017-05-31; 2017-08-17; 2017-09-21; 2017-11-22; 2017-11-29
| Hur många timmar finns tillgängliga? |  | nearU | bar: 2017-05-31; 2017-08-17; 2017-09-21; 2017-11-22; 2017-11-29
| Planera vilka moment/kort som ska utföras inom sprinten |  | Alla | bar: 2017-05-31; 2017-08-17; 2017-09-21; 2017-11-22; 2017-11-29
| Gå igenom utvalda kort för att se att inga direkt oklarheter finns |  | Alla | bar: 2017-05-31; 2017-08-17; 2017-09-21; 2017-11-22; 2017-11-29
| Revidera estimate av utvalda kort |  | nearU | bar: 2017-05-31; 2017-08-17; 2017-09-21; 2017-11-22; 2017-11-29
| Prioritera utvalda kort/moment |  | Ledarna | bar: 2017-05-31; 2017-08-17; 2017-09-21; 2017-11-22; 2017-11-29
Genomförande av sprint | bar: 2017-04-24 to 2017-04-28; 2017-05-02 to 2017-05-24; 2017-05-26 to 2017-06-22; 2017-06-26 to 2017-12-29
| Utveckling av planerade moment/kort enligt prioritering |  | nearU | bar: 2017-05-31 to 2017-06-22; 2017-06-26 to 2017-06-30; 2017-07-05 to 2017-07-07; 2017-07-12 to 2017-07-14; 2017-07-19 to 2017-07-21; 2017-07-26 to 2017-07-28; 2017-08-02 to 2017-08-17; 2017-08-30 to 2017-09-01; 2017-09-21; 2017-11-22; 2017-11-29
Regelbundna avstämningar
|  | nearU per dag | nearU | bar: 2017-05-31 to 2017-06-22; 2017-06-26 to 2017-06-30; 2017-07-05 to 2017-07-07; 2017-07-12 to 2017-07-14; 2017-07-19 to 2017-07-21; 2017-07-26 to 2017-07-28; 2017-08-02 to 2017-08-16
|  | Projektgruppen per vecka | Alla | bar: 2017-05-31; 2017-06-07; 2017-06-14; 2017-06-21; 2017-06-28; 2017-07-05; 2017-07-12
| Code review |  | nearU | bar: 2017-08-09
| nearU funktionstester |  | nearU | bar: 2017-06-28 to 2017-06-29; 2017-07-05 to 2017-07-06; 2017-07-12 to 2017-07-13; 2017-07-19 to 2017-07-20; 2017-07-26 to 2017-07-27; 2017-08-02 to 2017-08-16
| Justeringar efter funktionstester |  | nearU | bar: 2017-06-28 to 2017-06-29; 2017-07-05 to 2017-07-06; 2017-07-12 to 2017-07-13; 2017-07-19 to 2017-07-20; 2017-07-26 to 2017-07-27; 2017-08-03 to 2017-08-14
| Installation på kundtest/stage (?) |  | nearU | bar: 2017-08-04
Test och acceptans | [8 empty] | 2017-06-28: x; 2017-06-29: x; 2017-06-30: x; 2017-07-03: x; 2017-07-04: x; 2017-07-05: x; 2017-07-06: x; 2017-07-07: x; 2017-07-10: x; 2017-07-11: x; 2017-07-12: x; 2017-07-13: x; 2017-07-14: x; 2017-08-17: DS8; 2017-09-13: DS9; 2017-10-04: DS10
| Demo/genomgång av nya mallar och funktioner som ingår i sprinten |  | Alla | bar: 2017-06-28
| Ledarna acceptanstestar |  | Ledarna | bar: 2017-07-03 to 2017-07-05; 2017-07-10 to 2017-07-12
|  | Viss kommunikation sker löpande när testerna genomförs | Alla | bar: 2017-07-04 to 2017-07-06; 2017-07-11 to 2017-07-13
|  | Ledarna sammanställer felrapporter | Ledarna
|  | Justering, rättning och interntester görs | nearU
|  | Ledarna utför omtester | Ledarna
| Ledarna godkänner för installation |  | Ledarna
| Kodstopp införs |  | nearU
Sprintslut | [8 empty] | 2017-09-13: x; 2017-09-26: IS8; 2017-10-18: x
| Installation i produktionsmiljö utförs |  | nearU | [5 empty] | 2017-09-13: IS8 flyttas till --------------------------------------------->; 2017-09-26: IS9; 2017-10-18: IS10
|  | nearU meddelar att installationen påbörjas | nearU | bar: 2017-09-13; 2017-10-18
|  | nearU meddelar att installationen är slutförd | nearU | bar: 2017-09-13; 2017-10-18
| Ledarna testar i produktionsmiljö |  | Ledarna
Övrigt, löpande och inte kopplat till en sprint
Dokumentation av editläget
Utbildningar
Note on BE39: ====== ID#AAAAECA_1wI nearU (2019-12-23 09:07:13) Sprintdemo av delleverans så att Ledarna kan testa under sommaren?
Note on CO13: ====== ID#AAAAECA_1zM nearU (2019-12-23 09:07:13) Planering sprint 9
Note on CO38: ====== ID#AAAAECA_1y8 nearU (2019-12-23 09:07:13) Sprintdemo sprint 8
Note on DH38: ====== ID#AAAAECA_1so nearU (2019-12-23 09:07:13) Sprintdemo sprint 9
Note on DN13: ====== ID#AAAAECA_1ts nearU (2019-12-23 09:07:13) Planering sprint 10
Note on DQ48: ====== ID#AAAAECA_1wY nearU (2019-12-23 09:07:13) Installation sprint 8
Note on DQ49: ====== ID#AAAAECA_1ug nearU (2019-12-23 09:07:13) Installation sprint 9
Note on DW38: ====== ID#AAAAECA_1v0 nearU (2019-12-23 09:07:13) Demo sprint 10
Note on EG13: ====== ID#AAAAECA_1t4 nearU (2019-12-23 09:07:13) Planering av förberedelser och release?
Note on EG49: ====== ID#AAAAECA_1tI nearU (2019-12-23 09:07:13) Installation Sprint 10
Note on EL13: ====== ID#AAAAECA_1t8 nearU (2019-12-23 09:07:13) Planering av förberedelser och release?
Note on EM3: ====== ID#AAAAECA_1uw nearU (2019-12-23 09:07:13) Codefreeze
Note on FF13: ====== ID#AAAAECA_1yw nearU (2019-12-23 09:07:13) Eventuell planering efter release
Note on FK13: ====== ID#AAAAECA_1xE nearU (2019-12-23 09:07:13) Eventuell planering efter release